RELOAD

Phase 1.2 Pre-Launch Project Plan

"Not just tracking your emotions — helping you respond to them."

Prepared by: Kant Aung  |  Date: April 2026  |  Version: 1.0

# 1. Project Overview

Reload is a mobile-first emotional wellbeing app that goes beyond simple tracking. Where other apps stop at 'you feel anxious', Reload interprets patterns and offers behavioural responses. This document is the master project plan for Phase 1.2 — the final development sprint before public launch.

| App Name | Reload |
| --- | --- |
| Current Phase | 1.2 — Pre-Launch Sprint |
| Project Lead | Kant Aung |
| Total Steps | 10 steps across 5 workstreams |
| Estimated Duration | 12–14 weeks (3–3.5 months) |
| Target Launch | ~July / August 2026 |

## Core Positioning

Reload's Unique Value Proposition Most apps: "You are feeling anxious." Reload: "You've logged anxiety after social situations — this might be anticipation, not outcome. Try staying through the moment." This difference is the entire product. Reload is the next layer after awareness.

# 2. Master Timeline & Step Order

Steps are ordered by dependency logic — foundational UX must come first, then backend systems, then integrations, then compliance, then personalisation. This prevents rework and keeps the build coherent.

| # | Step | Duration | Target Date | Priority |
| --- | --- | --- | --- | --- |
| 1 | Fix UX Writing | 1 week | Week 1 | Critical |
| 2 | Proper UI Design & Spacing | 1.5 weeks | Weeks 1–2 | Critical |
| 3 | UX Visualisation & Flow Review | 1 week | Week 2–3 | High |
| 4 | Custom Emotion Defining Steps | 1 week | Week 3 | High |
| 5 | Short Behavioural Response System | 2 weeks | Weeks 4–5 | Critical |
| 6 | Real-Time Nagging System | 2 weeks | Weeks 6–7 | Critical |
| 7 | Emotion & Behaviour Pattern Insights | 2 weeks | Weeks 8–9 | High |
| 8 | Linking Custom Emotions with the 3S | 1 week | Week 10 | High |
| 9 | Login with Apple & Google | 1.5 weeks | Weeks 11–12 | Medium |
| 10 | Privacy Policy / Plan | 1 week | Week 12 | Medium |
| 11 | Personalisation Settings | 1.5 weeks | Weeks 13–14 | Medium |

Note: Steps 1–3 are parallel where possible. Steps 5–8 form the 3S core system and must run sequentially.

# 3. Step-by-Step Execution Guide

## Step 1 — Fix UX Writing

| Timeline | Week 1 (5 working days) |
| --- | --- |
| Priority | CRITICAL — Must be done before UI pass |

### What This Means

UX writing is every word the user sees: button labels, empty states, error messages, onboarding copy, tooltip text, and system prompts. Bad UX writing breaks trust before the user even tries a feature.

### Why It Must Come First

UI design pass (Step 2) must be done with final copy in place. If you redesign spacing around placeholder text, you'll have to redo it. Fix the words first, then wrap design around them.

### What to Audit

- Onboarding screens — are they welcoming, human, and clear about what Reload does?

- Emotion log prompt — replace 'Select category' with 'Help Reload understand this feeling'

- Response/nudge messages — do they sound like a smart friend, not a clinical form?

- Empty states — what does the app say when there's no data yet?

- CTA buttons — are they action-oriented? (e.g. 'Log Now', 'See My Patterns')

- Error messages — are they helpful and non-technical?

### UX Copy Principles for Reload

- Human over clinical — 'How are you holding up today?' beats 'Log emotional state'

- Specific over vague — 'You've logged anxiety 3x today' beats 'You seem stressed'

- Empowering over diagnostic — 'Try this' beats 'You are experiencing...'

- Short over long — max 2 lines for any in-app copy

### Prompt Template for This Step

Ready-to-Use AI Prompt "I am building a mobile wellbeing app called Reload. The app helps users track emotions and gives behavioural suggestions. I need you to rewrite all UX copy in the app to sound warm, human, and empowering — not clinical or robotic. Here is the current copy: [paste current strings]. Please rewrite each one keeping it under 2 lines, using second-person voice, and avoiding medical or diagnostic language. The brand tone is: a smart, kind friend who knows psychology."

## Step 2 — Proper UI Design & Spacing

| Timeline | Weeks 1–2 (overlaps with Step 1 audit) |
| --- | --- |
| Priority | CRITICAL — Defines first impression |

### What This Means

This is the visual polish pass. After UX writing is fixed, you systematically go screen-by-screen and apply consistent spacing, hierarchy, padding, and visual rhythm. The goal is not to redesign — it is to make what exists feel considered and professional.

### Key Areas

- Consistent padding: 16px or 20px margin on all screen edges

- Touch targets: all buttons and tappable areas minimum 44x44px

- Typography scale: clear hierarchy (Title > Subheading > Body > Caption)

- Colour use: emotion colours consistent across log, chart, and nudge system

- Spacing between components: no cramped sections, no orphaned elements

- Card design: emotion log cards, nudge cards, and insight cards all unified

- Loading states: skeleton loaders or spinners on all async screens

### Spacing System to Lock In

- Base unit: 8px — all spacing in multiples of 8 (8, 16, 24, 32, 48)

- Screen edge padding: 20px left/right

- Section gap: 32px between major sections

- Component internal padding: 16px

- List item gap: 12px

### Prompt Template for This Step

Ready-to-Use AI Prompt "I am working on a React Native / React app called Reload — a mobile wellbeing app. I need help doing a systematic UI spacing and design pass. Here is my current component [paste component code]. Please: (1) apply an 8px base spacing grid, (2) ensure all touch targets are 44px minimum, (3) add consistent padding, (4) improve visual hierarchy with proper font sizes and weights, (5) make it feel polished on mobile. Return the updated component code with inline comments explaining each change."

## Step 3 — UX Visualisation & Flow Review

| Timeline | Weeks 2–3 (3–4 days) |
| --- | --- |
| Priority | HIGH — Catches flow issues before 3S build |

### What This Means

Before building the 3S systems, you need to map all user flows as if you are a first-time user. This catches broken journeys, dead ends, and confusing transitions before they are baked into the response logic.

### Flows to Map

- Onboarding flow — first open to first log

- Emotion log flow — from dashboard to post-log response

- Custom emotion creation flow — naming, tagging, energy mapping

- Nudge delivery flow — how/when nudges appear mid-session

- Pattern insight access — where users find weekly insights

- Settings flow — how users access personalisation

### How to Execute

Use Figma, FigJam, or even a paper sketch. For each flow, answer: (1) What is the user trying to do? (2) What is the first thing they see? (3) What are all the paths? (4) What happens if something goes wrong? (5) Where do they end up?

### Prompt Template for This Step

Ready-to-Use AI Prompt "I am reviewing UX flows for Reload, a mobile emotional wellbeing app. The core feature is emotion logging followed by behavioural suggestions. Here are my current screen names and navigation structure: [paste screen list]. Please map the user journey for [specific flow], identify any dead ends, confusing transitions, or missing states (empty, error, loading), and suggest improvements. Format as a numbered flow with annotations."

## Step 4 — Defining Steps for Custom Emotions

| Timeline | Week 3 (3–4 days) |
| --- | --- |
| Priority | HIGH — Gates the entire 3S system |

### What This Means

Custom emotions are a strategic differentiator. Where other apps give a fixed list, Reload lets users name their own feelings — but still maps them to a structured internal model so the 3S can act on them intelligently.

### The Tagging Model (Lock This In)

When a user creates a custom emotion, Reload asks 2 micro-questions:

Custom Emotion Creation Flow Step 1 — Category mapping: "Does this feel more like:" [ Anxiety ] [ Sadness ] [ Anger ] [ Low Energy ] [ High Energy ] [ Happiness ] [ Motivation ] [ Something else ] Step 2 — Energy level: "Energy level right now:" [ Low ] [ Medium ] [ High ] UX copy under the question: "This helps Reload give you better suggestions" Time to complete: 2–3 seconds maximum

### Internal Data Structure

Each custom emotion stores: { label: 'Frazzled', category: 'anxiety', energy: 'high', valence: 'negative', userId: '...' }

This gives the response system everything it needs to match predefined emotions in behaviour.

### UX Copy Rules

- Never say 'Select category' — say 'Help Reload understand this feeling'

- Never say 'Tag your emotion' — say 'This helps us give better suggestions'

- Make it feel like the app is curious, not bureaucratic

- Never make users feel 'wrong' about the word they chose

### Prompt Template for This Step

Ready-to-Use AI Prompt "I am building a custom emotion creation feature for a wellbeing app called Reload. When a user creates a new custom emotion (e.g. 'Frazzled'), the app asks 2 quick questions to map it internally: (1) which emotional category it resembles, and (2) energy level. I need: (a) the React component for this 2-step micro-flow with smooth animation between steps, (b) the data model to store the result, (c) a function that maps custom emotions to system categories, (d) UX copy that feels warm and human — not like a form. The app uses [your stack e.g. React Native / Tailwind]."

## Step 5 — Short Behavioural Response System (After Log)

| Timeline | Weeks 4–5 (core 3S build, Step 1 of 3) |
| --- | --- |
| Priority | CRITICAL — This is Reload's primary differentiator |

### What This Means

Every time a user logs an emotion, Reload shows a short behavioural response — a 1–2 line message that interprets the emotion and offers a concrete micro-action. This is what separates Reload from every tracker that just says 'you feel anxious'.

### Response Logic

Responses are generated based on 3 factors:

- Category — what type of emotion (anxiety, anger, low energy, etc.)

- Energy level — high, medium, or low

- Frequency — how many times this emotion has been logged recently (today / this week)

### Response Examples

Example Responses by Scenario Emotion: Anxiety ¦ Energy: High ¦ First log today Response: "This might be anticipation more than outcome — try staying present rather than avoiding the situation." Emotion: Anxiety ¦ Energy: High ¦ 3rd log today Response: "You've logged anxiety 3 times today. A short reset might help before continuing." Emotion: Low Energy ¦ Energy: Low ¦ Evening Response: "Low energy is common at this time of day. Consider lighter goals for the next hour." Emotion: Anger ¦ Energy: High ¦ 2nd log this session Response: "High-energy states can feel urgent. Pausing briefly often changes what feels necessary."

### Data Needed

- Emotion category and energy level (from log or custom emotion tag)

- Log frequency counter (session + daily)

- Time of day (optional but powerful for contextual responses)

### Response Library

Build a response library with 3–5 messages per combination (category x energy x frequency bucket). This prevents repetition and keeps responses feeling fresh. Start with ~60 messages covering the most common combinations.

### Prompt Template for This Step

Ready-to-Use AI Prompt "I am building the Short Behavioural Response System for Reload, a wellbeing app. After a user logs an emotion, the app shows a 1–2 sentence response that interprets the feeling and suggests a micro-action. Responses are based on: (1) emotion category [anxiety/sadness/anger/low energy/high energy/happiness/motivation], (2) energy level [low/medium/high], (3) log frequency today [first, second, third+]. Please generate a response library of 3 responses per combination for the following combinations: [list combinations]. Responses must sound like a knowledgeable, warm friend — not clinical. They should acknowledge, interpret briefly, and suggest one small action. Maximum 2 sentences."

## Step 6 — Real-Time Nagging System

| Timeline | Weeks 6–7 (core 3S build, Step 2 of 3) |
| --- | --- |
| Priority | CRITICAL — Creates habit loops |

### What This Means

The nagging system (or 'nudge system') monitors emotional data in real time during a session and proactively intervenes when patterns are detected. Unlike Step 5 which responds to a single log, this responds to accumulating patterns within a session.

### Trigger Logic

- Trigger 1 — Frequency spike: same negative emotion logged 3+ times in a session

- Trigger 2 — Escalation: emotion intensity or energy escalating across logs

- Trigger 3 — Prolonged negative state: negative emotion dominant for 2+ hours

- Trigger 4 — Time-based: it's late evening and only negative states logged today

### Nudge Examples

Real-Time Nudge Examples Trigger: Anxiety logged 3x in one session Nudge: "You've been logging high-energy stress today — a short pause might help before continuing." Trigger: 3 hours since last positive emotion logged Nudge: "You haven't logged anything positive in a while. Is there a small win from today?" Trigger: Evening + 4 negative logs Nudge: "Your evening is carrying a lot today. Winding down earlier might help tomorrow feel lighter."

### Technical Implementation

- Store session logs in state with timestamps

- Run trigger evaluation function after every new log

- Use a 'nudge cooldown' — minimum 45 minutes between nudges to prevent over-nagging

- Allow user to dismiss nudges and track dismissal patterns

- Nudges appear as a non-blocking overlay or bottom sheet — never full screen interruption

### Prompt Template for This Step

Ready-to-Use AI Prompt "I am building a real-time nudge system for Reload, a wellbeing app. The system monitors emotion logs during a session and triggers a gentle nudge message when certain patterns are detected. Triggers include: (1) same negative emotion 3+ times in a session, (2) no positive emotion logged in 3+ hours, (3) escalating emotional intensity. Please write: (a) the trigger evaluation function in JavaScript/React that checks session log data after each new log, (b) a nudge message library for each trigger type (3 variations each), (c) a cooldown manager that prevents nudges firing more than once per 45 minutes, (d) a dismissable nudge UI component as a bottom sheet. The tone must be gentle, non-judgmental, and helpful."

## Step 7 — Emotion & Behaviour Pattern Insight System

| Timeline | Weeks 8–9 (core 3S build, Step 3 of 3) |
| --- | --- |
| Priority | HIGH — Weekly value driver, retention feature |

### What This Means

The insight system analyses accumulated log data (across days and weeks) and surfaces plain-language observations about the user's emotional patterns. Unlike a chart, this translates data into meaning.

### Insight Types

- Time patterns: 'Your low-energy states appear most in the evenings'

- Behaviour correlation: 'Low mood days in your log have fewer completed actions'

- Trigger patterns: 'Anxiety appears most frequently after social situations'

- Progress insights: 'You logged 3 fewer negative emotions this week than last'

- Positive momentum: 'Your motivation logs have doubled this week'

### Insight Generation Logic

- Aggregate last 7 days of logs by category, energy, time of day

- Find the dominant emotion category (highest frequency)

- Find time-of-day correlation (morning/afternoon/evening split)

- Compare this week vs last week for progress framing

- Generate plain-language sentence using template + data values

- Surface 2–3 insights per weekly summary — never more

### Prompt Template for This Step

Ready-to-Use AI Prompt "I am building the Pattern Insight System for Reload, a wellbeing app. It analyses 7-day emotion log data and produces 2–3 plain-language insight statements shown on a weekly dashboard. Here is the data structure of a log entry: { emotion: string, category: string, energy: 'low'¦'medium'¦'high', timestamp: ISO string, tags: string[] }. Please write: (a) an insight generation function that takes an array of log entries and returns 2–3 insight strings, (b) logic to detect time-of-day patterns, dominant emotion, and week-on-week change, (c) 10 insight sentence templates with variable slots (e.g. '{dominant_emotion} appears most in your {time_of_day} — lighter goals during this time may help'). Insights must read as human observations, not data summaries."

## Step 8 — Linking Custom Emotions with the 3S

| Timeline | Week 10 (integration week) |
| --- | --- |
| Priority | HIGH — Completes the custom emotion loop |

### What This Means

Once custom emotions have been tagged (Step 4) and the 3S systems are built (Steps 5–7), this step connects them. Custom emotions must flow through the same response, nudge, and insight logic as predefined emotions.

### The Three Links to Build

- Custom emotion -> Short Behavioural Response: map custom emotion's category tag to the correct response bucket from Step 5

- Custom emotion -> Nudge trigger: custom emotions with negative valence count toward trigger thresholds from Step 6

- Custom emotion -> Pattern Insights: custom emotions aggregate by their mapped category in weekly analysis from Step 7

### Technical Notes

The key is the mapping layer. Build a resolveEmotion(emotionId) function that returns { category, energy, valence } whether the emotion is predefined or custom. Every 3S function calls this resolver before acting.

### Testing Checklist

- Create a custom emotion 'Frazzled' mapped to anxiety/high energy/negative

- Log it 3 times and verify the nudge triggers correctly

- Check it appears in weekly insights under the anxiety category

- Verify the short response matches an anxiety/high-energy response template

### Prompt Template for This Step

Ready-to-Use AI Prompt "I have built: (1) a custom emotion creation system that tags emotions with category, energy, and valence; (2) a short behavioural response system that fires after log; (3) a real-time nudge system; (4) a pattern insight system. I now need to connect custom emotions to all three systems. Please write a resolveEmotion(emotionId, emotionStore) function that returns a normalised { category, energy, valence } object for both predefined and custom emotions. Then show how each of the 3 systems should call this resolver before processing, with example code snippets for each."

## Step 9 — Login with Apple & Google

| Timeline | Weeks 11–12 |
| --- | --- |
| Priority | MEDIUM — Required for launch, not core differentiation |

### What This Means

Authentication via Apple and Google OAuth reduces friction at sign-up and meets user expectations for a polished app. It also enables data persistence across devices and future sync features.

### Why This Order (After 3S)

Auth is infrastructure. If you build it too early, you can accidentally gate features behind login that should be accessible without it. Build the product first, then wrap auth around it once flows are stable.

### Implementation Steps

- Set up OAuth credentials in Apple Developer Console and Google Cloud Console

- Install auth library (e.g. NextAuth, Firebase Auth, Expo AuthSession, or Supabase Auth)

- Build sign-in screen with Apple and Google buttons (follow Apple HIG for button styling)

- Handle auth state globally and protect private routes

- Link auth user ID to emotion log data

- Test login, logout, and account recovery flow on both iOS and Android

### Important: Apple Sign-In Requirements

Apple requires that any app offering social login (Google, Facebook, etc.) MUST also offer Sign in with Apple. Non-compliance blocks App Store approval. Apple button must always be displayed at least as prominently as other social login buttons.

### Prompt Template for This Step

Ready-to-Use AI Prompt "I am adding Sign in with Apple and Sign in with Google to a React / React Native app called Reload. I am using [your auth library, e.g. Supabase / Firebase / NextAuth]. Please provide: (a) the complete sign-in screen component with correctly styled Apple and Google buttons per Apple HIG guidelines, (b) the auth configuration code, (c) a useAuth hook that exposes user state globally, (d) a protected route wrapper, (e) the function that links the authenticated user ID to the existing emotion log data store. Handle loading, error, and success states."

## Step 10 — Privacy Policy / Privacy Plan

| Timeline | Week 12 (parallel with Step 9 testing) |
| --- | --- |
| Priority | MEDIUM — Legal requirement for app store submission |

### What This Means

Both the Apple App Store and Google Play require a privacy policy for apps that collect personal data. Reload collects emotional data, timestamps, and auth data — all of which must be disclosed. This is not optional.

### Minimum Required Sections

- What data is collected (emotion logs, timestamps, auth tokens, device info)

- How data is stored (on-device vs cloud, encryption standard)

- Who data is shared with (third parties, analytics tools)

- How users can delete their data

- Contact information for data requests

- Last updated date

### Privacy Plan (If Full Policy Is Delayed)

A privacy plan is an internal document that commits to your data handling principles before the public policy is finalised. It protects you during beta and ensures the policy, when written, reflects actual practice.

### Emotional Data Is Sensitive Data

Emotional and mental health data is classified as sensitive personal data under GDPR. If you have UK or EU users, GDPR compliance is required. Key principles: collect only what you need, store securely, allow deletion on request.

### Prompt Template for This Step

Ready-to-Use AI Prompt "I need to write a Privacy Policy for Reload, a mobile wellbeing app that collects: emotion logs (text labels, category, energy level, timestamps), optional tags and notes, and authentication data (name and email from Apple/Google Sign-In). The app is developed in the UK and targets users in the UK and internationally. The policy must comply with GDPR and UK data protection law, and meet Apple App Store and Google Play requirements. Please draft a complete, plain-English privacy policy with the following sections: data collected, how it is used, storage and security, data sharing, user rights and deletion, contact details. Keep the language simple and reassuring."

## Step 11 — Personalisation Settings

| Timeline | Weeks 13–14 (final feature before launch) |
| --- | --- |
| Priority | MEDIUM — Enhances retention and reduces churn |

### What This Means

Personalisation gives users control over their experience and makes the app feel tailored. It also reduces irritation (e.g. users who find nudges too frequent) and increases long-term engagement.

### Core Settings to Include at Launch

- Nudge frequency — Off / Low (once/day) / Medium (3x/day) / High (as detected)

- Log reminder time — optional daily reminder at user-chosen time

- Insight delivery — weekly summary notification on/off

- Theme — Light / Dark / System

- Display name — how the app addresses the user

- Emotion display — compact or expanded emotion grid

### Settings to Add Post-Launch

- Favourite emotions — pin most-used emotions to top of log screen

- Goals and focus areas — link logging to personal wellbeing goals

- Export data — download emotion history as CSV or PDF

### UX Notes for Settings

Settings should feel like preferences, not configuration. Group into: 'Notifications', 'Appearance', 'About Me'. Use toggles and sliders over dropdowns. Preview changes live where possible.

### Prompt Template for This Step

Ready-to-Use AI Prompt "I am building the personalisation settings screen for Reload, a mobile wellbeing app. Settings include: nudge frequency (off/low/medium/high), daily log reminder time picker, weekly insight notification toggle, light/dark/system theme toggle, and display name input. Please build: (a) the settings screen UI in React/React Native using clean mobile design patterns, (b) a settings context/hook that persists settings to local storage and makes them available globally, (c) integration points showing how the nudge frequency setting is read by the nudge system from Step 6. All settings must persist across sessions."

# 4. Pre-Launch Checklist

Complete all items before submitting to App Store / Play Store.

## Product

- All 11 steps above completed and tested

- No critical bugs in core log -> response flow

- Custom emotions map correctly through all 3 systems

- Nudge cooldown working correctly (no spam)

- Empty states designed for all screens

## Design

- UI consistent across all screens

- Dark mode working

- Tested on at least 3 screen sizes

- Loading and error states on all async operations

## Auth & Data

- Apple Sign-In working on iOS

- Google Sign-In working on Android and iOS

- User data persists correctly after logout/login

- Data deletion flow works end-to-end

## Legal & Compliance

- Privacy Policy live at accessible URL

- Privacy Policy linked from app settings and App Store listing

- App Store metadata and screenshots ready

- GDPR data handling reviewed

# 5. Strategic Positioning Reminder

As you build, return to this frame whenever a decision feels unclear.

The Core Positioning Reload is not a mood tracker. Reload is a response system. Other apps: "You feel anxious." Reload: "You've felt anxious after social situations — try staying present instead of avoiding." Compete on: insight quality, usefulness, and the feeling 'this app gets me'. Do not compete on: number of emotions, scientific branding, or journaling depth. Your unique edge: real NHS + applied psychology + research mindset. Most apps simulate psychology. You actually understand the mechanisms.

End of Reload Phase 1.2 Project Plan